## Sheet1
Quiz Generator Web Application
Start Date: - 20th June 2022 | End Date: -
Requirement Gathering | :- | Features User want: - | 3 types of login | students | teachers | admin
|  |  | student | login | subject -> test | not given
|  |  | teachers | profile | students crediential
|  |  | admin | test history | mail - credientials + link
block or delete student
profile
test history
Tools & Technologies | : - | IDE | Designing Tools | Server | Technologies | Database | Languages | Version Control System | Remote Repository
|  | Eclipse | Visual Code Studio | Apache TOMCAT | Servlets | MySQL | Java | Git | GitHub
|  |  | Live Server(Extension) |  | JSP | JDBC Connector | HTML
[5 empty] | Log4j(For Logging) |  | CSS
[5 empty] | JSON |  | JavaScript
Feasibility Test | : - | The web application is feasible as we have already created a prototype for a desktop application. We have to add additional features that the client want.
Desgin on Paper (Layout) | : - | Expected Time: - 5-6 Days |  | Time Taken : - 3 Week
Prototype Creation (GUI) | : - | Expected Time: - 2 Week
Database Design | : - | Expected Time: - 4 - 5 Days
Decide Layers | : - | Expected Time : - 2 - 3 Days
Classes & Method Desgin | : - | Expected Time : - 4 -5 Days
Coding | : - | Expected Time: - 3 - 4 Week
Testing & Re-work | : - | Expected Time : - 1 - 2 Week
UAT (User Accepting Test) | : - | Expected Time : - 3 - 4 Days
Final Release | : - | Expected Time : - 1 Day
Support & Service | : -